## 1 Summary
EDRMS Utilization Report - RAC Decision Summary ¦ Source: EDRMS_Utilization_Dashboard_Checker_7.xlsx ¦ 21 September 2026
RAC Decision | Bank-wide Oversight | Department Insights | Total | What it means for the build
Agreed | 14 | 44 | 58 | Build as specified.
Agreed with Changes | 5 | 4 | 9 | Build, but the specification has moved. See the Agreed with Changes sheet.
Needs Clarification | 17 | 5 | 22 | Do not build yet. Answers and recommendations on the Clarifications sheet.
Not Required | 6 | 10 | 16 | Remove from the prototype. See the Remove sheet.
Deferred | 23 | 20 | 43 | Out of scope for this release. See the Deferred sheet.
TOTAL | 65 | 83 | 148 | Items carrying a RAC decision.
Reading notes
Where the decisions are | Only two sheets in Checker 7 carry a RAC Decision column: Bank-wide (RAC), 65 items, and Department Insights (RAC), 83 items.
What is not decided | Project Insights, Institutional File Plan, Retention and Disposal, and Records and Archive Holdings have no decision column in Checker 7. Nothing on those four dashboards is finalized.
Read the shape first | Department Insights is effectively signed off: 44 of 83 items are clean Agreed. Bank-wide Oversight is not: only 14 of 65 are clean Agreed, and 40 of 65 are deferred or unresolved.
Build order | Build Department Insights now. Cut Bank-wide back to the items that survived. Build nothing on Retention and Disposal; it is the dependency blocking 25 deferred items.
The one blocking question | What counts as an EDRMS user (Bank-wide #2). It gates Bank-wide #2, #23, #24, #61, #62 and Department #3. RAC comments point to a rounded contextual headcount, not a measured figure. Confirm before wiring any user tile.
The global rename | Division is replaced by Department / Office / RM / RO everywhere. Division has no source: the Cloud Governance export carries a Division column and it is empty on all 1,032 EDRMS sites.
The global filter | Every count is limited to EDRMS-compliant sites, counted once per site, with project sites excluded from bank-wide totals.

## 2 All Decisions
Every item with a RAC decision, both dashboards, in checker order
Dashboard | # | Section | Requirement Item | RAC Decision | Feasibility Note (AvePoint) | RAC Comment
Bank-wide Oversight | 1 | Top Panel | Number of active EDRMS SharePoint sites for Department, RM, office Changes: 8/28/2026: Number of active EDRMS SharePoint sites for Department HQ | Agreed with Changes | Feasible Source: EDRMS DB Comments: Need to Backfill Department, Division, and RM values | Show one bank-wide count of active EDRMS-compliant department, office, RM and RO sites, counted once per site and excluding project sites. Keep the organizational breakdown in Department Insights. Backfill and maintain the required site classification metadata.
Bank-wide Oversight | 2 | Top Panel | Total number of EDRMS users | Needs Clarification | Define: 1. Someone who has declared a record? (Feasible) 2. User with access to EDRMS sites? (For feasibility check) | Show rounded number of people per department / office / RM. The number should indicate the size of the department / office / RM for context. The number does not need to be exact and therefore should not need to be regularly updated. E.g. CSD approx. 400 / SPSO approx 10..
Bank-wide Oversight | 3 | Top Panel | Total number of documents in EDRMS | Agreed | Feasible Source: SPO Log + CG | Show the total documents held in EDRMS-compliant sites, whether declared as records or not. Count each document once and exclude non-EDRMS and project sites from this total.
Bank-wide Oversight | 4 | Top Panel | Total number of records declared in EDRMS | Agreed | Feasible Source: EDRMS DB | Show the total number of records declared in all EDRMS sites.
Bank-wide Oversight | 5 | Top Panel | Total number of physical counterparts identified | Deferred | Feasible Source: EDRMS DB | Defer until the Retention and Disposal dashboard and related process are defined. Later reporting should distinguish overdue, due today and upcoming records, and account for retention extensions.
Bank-wide Oversight | 6 | Top Panel | Total number of records due for disposal | Deferred | Feasible Source: EDRMS DB Comments: All records have a due date for disposal; what does due for disposal mean? Due in the next 30/60/90 days? Or due for dispotal today (day of when the report is viewed) | Retain as a future navigation link, but do not include it in the current top panel until the Retention and Disposal dashboard is established.
Bank-wide Oversight | 7 | Top Panel | Retention and disposal insights (navigation tile) | Deferred |  | Retain as a future navigation link, but do not include it in the current top panel until the Institutional File Plan dashboard is established.
Bank-wide Oversight | 8 | Top Panel | Institutional File Plan insights (navigation tile) | Agreed
Bank-wide Oversight | 9 | Top Panel | Total number of active EDRMS SharePoint sites for Sovereign projects | Deferred | OOS | Defer until sovereign project sites and Project Insights are implemented and a reliable site-to-project classification is available.
Bank-wide Oversight | 10 | Top Panel | Total number of active EDRMS SharePoint sites for Nonsovereign projects | Deferred | OOS | Defer until nonsovereign project sites and Project Insights are implemented and a reliable site-to-project classification is available.
Bank-wide Oversight | 11 | Overview Of Edrms Sites | Department / office / RM Changes: 8/28/2026: Number of active EDRMS SharePoint sites for Department HQ and this change applies to all same columns as well | Agreed with Changes | Feasible Source: EDRMS DB Comments: Need to Backfill Department and Division values | Use Department / Office / RM / RO, regardless of physical location (not just HQ). To AvePoint: to confirm how “applies to all same columns” will be implemented.
Bank-wide Oversight | 12 | Overview Of Edrms Sites | Number of EDRMS SharePoint sites | Agreed | Feasible Source: CG
Bank-wide Oversight | 13 | Overview Of Edrms Sites | Total number of documents | Needs Clarification | Feasible Source: SPO | What does AvePoint mean by 'unit'? This shows the total number of documents for the department.
Bank-wide Oversight | 14 | Overview Of Edrms Sites | Total number of records declared | Needs Clarification | Should be same as S/N 4 right? | Same as item 13
Bank-wide Oversight | 15 | Overview Of Edrms Sites | Total number of physical counterparts | Needs Clarification | Should be same as S/N 5 right? | Dependent on item 14
Bank-wide Oversight | 16 | Overview Of Edrms Sites | Indicator: no. of sites created | Not Required | Feasible Source: CG Comments: Is this just EDRMS sites? | Remove as a duplicate of item 1. All dashboard counts must be limited to EDRMS-compliant sites.
Bank-wide Oversight | 17 | Overview Of Edrms Sites | Indicator: no. of sites deleted | Deferred | Feasible Source: CG Comments: Is this just EDRMS sites? | Defer as a possible future lifecycle metric. If retained, limit it to EDRMS-compliant sites and place it in Department Insights rather than the bank-wide top panel.
Bank-wide Oversight | 18 | Overview Of Edrms Sites | Indicator: no. of sites archived | Deferred | Feasible Source: CG Comments: Is this just EDRMS sites? | Defer until EDRMS sites begin moving to inactive or archived status. If retained, limit it to EDRMS-compliant sites and show it in Department Insights.
Bank-wide Oversight | 19 | Overview Of Edrms Sites | Indicator: inactive site for 90 days | Agreed with Changes | Feasible Source: CG Comments: Is this just EDRMS sites? | Retain as a Department Insights metric, not a bank-wide top-panel tile. Define inactivity using the available site-activity window and limit the measure to EDRMS-compliant sites.
Bank-wide Oversight | 20 | Sovereign And Nonsovereign | Sovereign project site list, all columns | Deferred | oos | Defer until sovereign project sites, the Project Insights dashboard and supporting site-to-project data are available.
Bank-wide Oversight | 21 | Sovereign And Nonsovereign | Nonsovereign project site list, all columns | Deferred | oos | Defer until nonsovereign project sites, the Project Insights dashboard and supporting site-to-project data are available.
Bank-wide Oversight | 22 | Sovereign And Nonsovereign | Project rows clickable into Project Insights | Deferred | oos | Defer the drill-through behavior until Project Insights is implemented.
Bank-wide Oversight | 23 | Users | Total number of users, count | Needs Clarification | to check feasibility Source: SPO Comments: Is this user with access to EDRMS sites? | Show rounded number of people per department / office / RM. The number should indicate the size of the department / office / RM for context. The number does not need to be exact and therefore should not need to be regularly updated. E.g. CSD approx. 400 / SPSO approx 10.
Bank-wide Oversight | 24 | Users | Departments, offices and RMs in the list | Needs Clarification | Feasible Source: CG/ EDRMS DB Comments: even without existing edrms sites? | See #23
Bank-wide Oversight | 25 | Users | Indicator: never accessed EDRMS | Needs Clarification | to check feasibility Source: SPO Comments: Is this user with access to EDRMS sites but have never opened the site? | If it's feasible? Data to know how many users within the department have not accessed the site, for compliance.
Bank-wide Oversight | 26 | Users | Indicator: not accessed in 90 days | Needs Clarification | to check feasibility Source: SPO Comments: Is this user with access to EDRMS sites but have never opened the site? | If it's feasible? Data can be used as a site inactivity measure (see item #19)
Bank-wide Oversight | 27 | Users | Total number of users (staff) | Needs Clarification | Not feasible for now Source: TBD Comments: is this for users who have access to edrms sites? If yes, what is the unique identifier for staff/ contractor/ consultant? Might need to access adb hr db | From Active Directory; is it possible to extract this information (see item #23)
Bank-wide Oversight | 28 | Users | Total number of users (Contractors) | Needs Clarification | Not feasible for now Source: TBD Comments: is this for users who have access to edrms sites? If yes, what is the unique identifier for staff/ contractor/ consultant? Might need to access adb hr db | From Active Directory; is it possible to extract this information (see item #23)
Bank-wide Oversight | 29 | Users | Total number of users (Consultants) | Needs Clarification | Not feasible for now Source: TBD Comments: is this for users who have access to edrms sites? If yes, what is the unique identifier for staff/ contractor/ consultant? Might need to access adb hr db | From Active Directory; is it possible to extract this information (see item #23)
Bank-wide Oversight | 30 | Users | Completion of training | Agreed | Do we have a maintained list of users that have access to edrms who have gone through training? How often is the list updated? Where is it hosted? Does it have the email addresses of the users? | Retain for RAC compliance monitoring. Use Excellerate for staff and the maintained completion source for contractors/consultants, with manual updates until an authoritative integration is available. Show completion against the relevant population.
Bank-wide Oversight | 31 | Users | Onboarded since go-live | Deferred | What does this mean? Not feasible for now. No metadata/identifier available to determine the go live date | Defer until RAC maintains an authoritative onboarding register and a reliable EDRMS go-live date for each site or unit.
Bank-wide Oversight | 32 | Documents | Number of documents created / uploaded | Agreed | Feasible Source: SPO Activity
Bank-wide Oversight | 33 | Documents | Documents size (in GB) | Needs Clarification | Need to check feasibiltiy | If feasible, yes. If not, can be removed.
Bank-wide Oversight | 34 | Documents | Number of users creating documents | Not Required | Users creating documents in SPO? Not including people uploading in SPO? Need to check feasibility if can retrieve in SPO | Remove. This overlaps with document totals and does not support the agreed RAC definition of an EDRMS user.
Bank-wide Oversight | 35 | Documents | Indicator: new documents month on month | Agreed with Changes | Need to check feasibiltiy Source: SPO Comments: Files created and uploaded? Or created only? Can have creation date as basis | Generation of report on total, not the growth (Show periodic snapshots or trend of total documents added, using files created and uploaded and the creation date. Report by Department / Office / RM / RO.)
Bank-wide Oversight | 36 | Documents | Indicator: average monthly storage growth | Agreed | dependent with S/N 33
Bank-wide Oversight | 37 | Documents | Per division breakdown | Not Required | If all can be retrieved, we need a division value for the documents, if these are declared documents, we need to source it from the EDRMS DB (provided that division backfill is done), if not a declared record, the file must have a metadata for division, if not, we can base it of the site it is hosted in | Remove the separate per-division breakdown. Use Department / Office / RM / RO groupings
Bank-wide Oversight | 38 | Records Declared | Total number of records declared | Agreed | Same with S/N 4
Bank-wide Oversight | 39 | Records Declared | Total number of users declaring records | Agreed | feasible Source: EDRMS DB
Bank-wide Oversight | 40 | Records Declared | Indicator: zero record declarations | Not Required | is this zero records in an edrms site? Department? Division? | This can be achieved by #38 & #39
Bank-wide Oversight | 41 | Records Declared | Indicator: declaration rate against documents | Agreed
Bank-wide Oversight | 42 | Records Declared | Number of records declared per division | Needs Clarification | Feasible Source: EDRMS DB Comments: Need to Backfill Department, Division values | Replace division with Department / Office / RM / RO. Provide filtering or drill-down rather than a separate division-only measure.
Bank-wide Oversight | 43 | Records Declared | Number of users declaring records per division | Needs Clarification | Feasible Source: EDRMS DB Comments: Need to Backfill Department, Division, and RM values; does a user have a division assigned to them? Or is this based on the site? Document? Etc | Replace division with Department / Office / RM / RO. Count unique people declaring records for the selected grouping.
Bank-wide Oversight | 44 | Physical Counterparts | Total number of physical records declared | Agreed | Same with S/N 5
Bank-wide Oversight | 45 | Physical Counterparts | Total number of users declaring records | Agreed
Bank-wide Oversight | 46 | Physical Counterparts | Share of records with a counterpart | Needs Clarification | is this % of Physical vs All records? Feasible | visualization: graph or just a tile containg %
Bank-wide Oversight | 47 | Physical Counterparts | Per division, two columns | Not Required | per division physical? Feasible | Remove the separate division columns. Use Department / Office / RM / RO filters
Bank-wide Oversight | 48 | Physical Counterparts | Indicator: physical counterpart completion rate (turned over to RAC) | Deferred | OOS for now, Need Physical Records Feature Release | Defer until the physical records management or Records and Archives Holdings capability records handover to RAC.
Bank-wide Oversight | 49 | Records Due For Disposal | Number of records due for disposal | Deferred | Same comment S/N 6 | Defer until the dashboard for Retention and Disposal is developed.
Bank-wide Oversight | 50 | Records Due For Disposal | Next due date for disposal | Deferred | Need to define S/N 6 to determine this | Defer until the dashboard for Retention and Disposal is developed.
Bank-wide Oversight | 51 | Records Due For Disposal | With physical counterpart? | Deferred | Need to define S/N 6 to determine this | Defer until the dashboard for Retention and Disposal is developed.
Bank-wide Oversight | 52 | Records Due For Disposal | Indicator: upcoming next quarter | Deferred |  | Defer until the dashboard for Retention and Disposal is developed.
Bank-wide Oversight | 53 | Records Due For Disposal | Disposal approver | Deferred | OOS for now, Need Records Disposition Feature Release | Defer until the dashboard for Retention and Disposal is developed.
Bank-wide Oversight | 54 | Records Due For Disposal | Status (Approved) | Deferred | OOS for now, Need Records Disposition Feature Release | Defer until the dashboard for Retention and Disposal is developed.
Bank-wide Oversight | 55 | Records Due For Disposal | Status (Declined) | Deferred | OOS for now, Need Records Disposition Feature Release | Defer until the dashboard for Retention and Disposal is developed.
Bank-wide Oversight | 56 | Records Due For Disposal | Status (Extended) | Deferred | OOS for now, Need Records Disposition Feature Release | Defer until the dashboard for Retention and Disposal is developed.
Bank-wide Oversight | 57 | Records Due For Disposal | Indicator: records disposed month on month | Deferred | OOS for now, Need Records Disposition Feature Release | Defer until the dashboard for Retention and Disposal is developed.
Bank-wide Oversight | 58 | Records Due For Disposal | Indicator: overdue actions, pending approvals | Deferred | OOS for now, Need Records Disposition Feature Release | Defer until the dashboard for Retention and Disposal is developed.
Bank-wide Oversight | 59 | Records Due For Disposal | Indicator: disposal completion rate | Deferred | OOS for now, Need Records Disposition Feature Release | Defer until the dashboard for Retention and Disposal is developed.
Bank-wide Oversight | 60 | The Rest Of Bank-Wide | Comparison, three named ratios: Documents against Records declared | Not Required | Feasible | Same as item 41?
Bank-wide Oversight | 61 | The Rest Of Bank-Wide | Comparison, three named ratios: Active users against documents | Needs Clarification | is this a ration of document per active user? Need to define active user | Replace active users with the available contextual workforce count by Department / Office / RM / RO, if sourced authoritatively, and compare it with document totals.
Bank-wide Oversight | 62 | The Rest Of Bank-Wide | Comparison, three named ratios: Active users against Records declared | Needs Clarification | is this a ration of document per active user? Need to define active user | Compare the contextual workforce count by Department / Office / RM / RO with declared records, if an authoritative workforce source is available.
Bank-wide Oversight | 63 | The Rest Of Bank-Wide | Bank-wide records declaration trend, cumulative | Agreed | feasible
Bank-wide Oversight | 64 | The Rest Of Bank-Wide | Records declared in range | Agreed | date range? Feasible | Show the count of records declared within a user-selected date range, with clear from/to controls and useful preset ranges.
Bank-wide Oversight | 65 | The Rest Of Bank-Wide | Monthly average in range | Agreed with Changes | date range? Average declared records? | This is a report. Not average. Show the number of records declared per month for the selected period, alongside the trend so peak periods and year-on-year patterns can be reviewed.
Department Insights | 1 | Department Profile | Department picker driving the whole screen | Agreed | For All: As long as Department, Division is back filled | Use Department / Office / RM / RO only
Department Insights | 2 | Department Profile | Total number of sites created | Agreed | Feasible EDRMS DB
Department Insights | 3 | Department Profile | Total number of EDRMS users | Agreed | Feasible EDRMS DB | Show rounded number of people per department / office / RM. The number should indicate the size of the department / office / RM for context. The number does not need to be exact and therefore should not need to be regularly updated. E.g. CSD approx. 400 / SPSO approx 10.
Department Insights | 4 | Department Profile | Total number of site visitors | Needs Clarification | Need to check feasibility SPO Activity Assuming sites per department selected | Can this be a number of unique users who accessed the site and is not with ADB email?
Department Insights | 5 | Department Profile | Total number of documents in EDRMS | Agreed | Feasible SPO Activity
Department Insights | 6 | Department Profile | Total number of records declared in EDRMS | Agreed | Feasible EDRMS DB
Department Insights | 7 | Department Profile | Total number of physical counterparts identified | Agreed | Feasible EDRMS DB
Department Insights | 8 | Department Profile | Total number of records due for disposal | Deferred | Similar question with Bank wide Oversite S/N 6 | Defer until Records Disposition feature is released.
Department Insights | 9 | Department Profile | Clickable top panel stats | Agreed
Department Insights | 10 | Department Profile | Approved SharePoint site, library and folder convention | Needs Clarification | Need to identify source and data model | Can this be just a link to the department's approved site convention to make it easily accessible for users
Department Insights | 11 | Department Profile | Go-Live date | Needs Clarification | Need to identify source | Can this be for manual input to record when a site was provisioned to a department
Department Insights | 12 | Users And Activity | Total number of active users | Agreed | Total Number of Active Users per Department - feasible CG + SPO
Department Insights | 13 | Users And Activity | Used EDRMS in the last 180 days | Agreed | Total Number of Active Users per Department - feasible CG + SPO
Department Insights | 14 | Users And Activity | No access in EDRMS compliant sites, last 180 days | Not Required | Opposite of S/N 13 - feasible | Remove as duplicative of the agreed inactivity measure in item 13.
Department Insights | 15 | Users And Activity | Never accessed EDRMS compliant sites | Not Required |  | Remove. The available reporting window cannot support the word 'never', and item 13 provides the needed inactivity view.
Department Insights | 16 | Users And Activity | Total number of staff | Deferred | Similar question with Bank wide Oversite S/N 27 | to align with the Bank-wide tab #27-29
Department Insights | 17 | Users And Activity | Total number of contractors (#, %) | Deferred | Similar question with Bank wide Oversite S/N 27 | to align with the Bank-wide tab #27-29
Department Insights | 18 | Users And Activity | Total number of consultants (#, %) | Deferred | Similar question with Bank wide Oversite S/N 27 | to align with the Bank-wide tab #27-29
Department Insights | 19 | Users And Activity | Training completion rate (%) | Agreed with Changes | Similar question with Bank wide Oversite S/N 30 | Retain for RAC compliance monitoring by selected grouping. Use authoritative training sources where available and allow controlled manual updates until integration is established.
Department Insights | 20 | Overview Of Edrms Sites | Total number of sites created | Agreed | feasible
Department Insights | 21 | Overview Of Edrms Sites | Total number of documents in EDRMS | Agreed | feasible
Department Insights | 22 | Overview Of Edrms Sites | Total number of records declared in EDRMS | Agreed | feasible
Department Insights | 23 | Overview Of Edrms Sites | Total number of physical counterparts identified | Agreed | feasible
Department Insights | 24 | Overview Of Edrms Sites | Total number of records due for disposal within 12 months | Deferred | feasible | Defer to the Retention and Disposal dashboard
Department Insights | 25 | Overview Of Edrms Sites | Name of sites | Agreed | feasible
Department Insights | 26 | Overview Of Edrms Sites | Site owners | Agreed | feasible
Department Insights | 27 | Overview Of Edrms Sites | Number of documents | Agreed | feasible
Department Insights | 28 | Overview Of Edrms Sites | Number of records | Agreed | feasible
Department Insights | 29 | Overview Of Edrms Sites | Number of physical counterparts | Agreed | feasible
Department Insights | 30 | Overview Of Edrms Sites | Number of records due for disposal | Deferred | Similar question with Bank wide Oversite S/N 6 | Defer to the Retention and Disposal dashboard
Department Insights | 31 | Site Visits | Total number of visitors | Not Required |  | Same as #4
Department Insights | 32 | Site Visits | Site visits table, by site | Agreed | Feasible SPO Activity
Department Insights | 33 | Site Visits | Page View Count | Not Required | Feasible SPO Activity
Department Insights | 34 | Site Visits | Visited Page Count | Not Required | Feasible SPO Activity
Department Insights | 35 | Site Visits | Name of sites | Not Required | Feasible SPO Activity | Same as #32
Department Insights | 36 | Site Visits | Page View Count | Not Required | Feasible SPO Activity
Department Insights | 37 | Site Visits | Visited Page Count | Not Required | Feasible SPO Activity
Department Insights | 38 | Site Visits | EDRMS Site Type | Agreed | Feasible EDRMS DB/ CG
Department Insights | 39 | Site Visits | Total number of visitors (external) (#, %) | Agreed | Need Source to identify if a user is Internal/ External | same as #4 and shows number of Non-ADB people who have accessed the site
Department Insights | 40 | Site Visits | Total number of visitors (internal) (#, %) | Agreed | Need Source to identify if a user is Internal/ External
Department Insights | 41 | Site Visits | Total number of access requests granted (#, %) | Needs Clarification | Need more details on what is meant by this | Is it possible to know how many access requests are granted, could be used as a basis to review the library's restriction
Department Insights | 42 | Site Visits | Total number of access requests denied (#, %) | Not Required | Need more details on what is meant by this
Department Insights | 43 | Total Number Of Documents In Edrms | Number of documents created / uploaded | Agreed | Feasible
Department Insights | 44 | Total Number Of Documents In Edrms | EDRMS Active Sites | Agreed | Feasible
Department Insights | 45 | Total Number Of Documents In Edrms | Total documents size | Agreed | Feasible
Department Insights | 46 | Total Number Of Documents In Edrms | Name of sites | Agreed | Feasible
Department Insights | 47 | Total Number Of Documents In Edrms | Number of documents created / uploaded | Agreed with Changes | Feasible | Show document count per site as the breakdown of item 43; ensure that this is not a duplicate the same metric elsewhere.
Department Insights | 48 | Total Number Of Documents In Edrms | Documents size (in GB) | Agreed | same concern with bank wide oversight | If feasible, yes. If not, can be removed.
Department Insights | 49 | Total Number Of Documents In Edrms | Number of users creating documents | Agreed | same concern with bank wide oversight | related to item #43
Department Insights | 50 | Records Declaration | Total number of records declared | Agreed | feasible
Department Insights | 51 | Records Declaration | Total number of users declaring records | Agreed | feasible
Department Insights | 52 | Records Declaration | Sites with no declared record in 180 days | Agreed | feasible
Department Insights | 53 | Records Declaration | Total number of records declared | Agreed | feasible
Department Insights | 54 | Records Declaration | Total number of users declaring records | Agreed | feasible
Department Insights | 55 | Records Declaration | Total declared record size (in GB) | Agreed | feasible | If feasible, yes. If not, can be removed.
Department Insights | 56 | Records Declaration | Number of records declared per division | Agreed with Changes | feasible | Replace division with Department / Office / RM / RO
Department Insights | 57 | Records Declaration | Number of users declaring records per division | Agreed with Changes | feasible | Replace division with Department / Office / RM / RO. Count unique declarers for the selected grouping
Department Insights | 58 | Physical Counterpart | Records with a counterpart | Agreed | feasible
Department Insights | 59 | Physical Counterpart | Total number of records declared | Agreed | feasible
Department Insights | 60 | Physical Counterpart | Records with a counterpart, by site | Agreed | feasible
Department Insights | 61 | Physical Counterpart | Total number of records declared | Agreed | feasible
Department Insights | 62 | Physical Counterpart | Share of records with a counterpart | Agreed | physical vs records
Department Insights | 63 | Physical Counterpart | Per division, two columns | Not Required | per division physical? Feasible | Remove separate division columns.
Department Insights | 64 | Physical Counterpart | Physical counterpart completion rate (turned over to RAC) | Deferred | OOS for now, Need Physical Records Feature Release | Defer until the physical records management or Records and Archives Holdings capability records handover to RAC.
Department Insights | 65 | Disposal | Records due for disposal within 3 months | Deferred | feasible | Defer until Records Disposition feature is released.
Department Insights | 66 | Disposal | Records due for disposal within 6 months | Deferred | feasible | Defer until Records Disposition feature is released.
Department Insights | 67 | Disposal | Records due for disposal within 12 months | Deferred | feasible | Defer until Records Disposition feature is released.
Department Insights | 68 | Disposal | Number of records due for disposal | Deferred | same concern with bank wide oversight S/N 6 | Defer until Records Disposition feature is released.
Department Insights | 69 | Disposal | Next due date for disposal | Deferred | Need to define above to determine this | Defer until Records Disposition feature is released.
Department Insights | 70 | Disposal | With physical counterpart? | Deferred | Need to define above to determine this | Defer until Records Disposition feature is released.
Department Insights | 71 | Disposal | Disposal approver | Deferred | OOS for now, Need Records Disposition Feature Release | Defer until Records Disposition feature is released.
Department Insights | 72 | Disposal | Status (Approved) | Deferred | OOS for now, Need Records Disposition Feature Release | Defer until Records Disposition feature is released.
Department Insights | 73 | Disposal | Status (Declined) | Deferred | OOS for now, Need Records Disposition Feature Release | Defer until Records Disposition feature is released.
Department Insights | 74 | Disposal | Status (Extended) | Deferred | OOS for now, Need Records Disposition Feature Release | Defer until Records Disposition feature is released.
Department Insights | 75 | Disposal | Total number of records disposed, per year and month | Deferred | OOS for now, Need Records Disposition Feature Release | Defer until Records Disposition feature is released.
Department Insights | 76 | Disposal | Total disposed record size (in GB) | Deferred | OOS for now, Need Records Disposition Feature Release | Defer until Records Disposition feature is released.
Department Insights | 77 | Departmental Library Usage, One Per File Plan Category | Library names | Agreed | feasible
Department Insights | 78 | Departmental Library Usage, One Per File Plan Category | Number of documents | Agreed | feasible
Department Insights | 79 | Departmental Library Usage, One Per File Plan Category | Number of records declared | Agreed | feasible
Department Insights | 80 | Departmental Library Usage, One Per File Plan Category | Number of physical counterparts | Agreed | feasible
Department Insights | 81 | Departmental Library Usage, One Per File Plan Category | Number of users per library | Agreed
Department Insights | 82 | Departmental Library Usage, One Per File Plan Category | Indicators per library, per division | Needs Clarification |  | Replace division with Department / Office / RM / RO
Department Insights | 83 | Other Panels On This Dashboard | Programme dates | Deferred |  | To finalize programmes to be included (go-live, site audit. etc.)

## 3 Agreed
Build as specified. No open question on these.
Dashboard | # | Section | Requirement Item | Source / Feasibility | RAC Comment
Bank-wide Oversight | 3 | Top Panel | Total number of documents in EDRMS | Feasible Source: SPO Log + CG | Show the total documents held in EDRMS-compliant sites, whether declared as records or not. Count each document once and exclude non-EDRMS and project sites from this total.
Bank-wide Oversight | 4 | Top Panel | Total number of records declared in EDRMS | Feasible Source: EDRMS DB | Show the total number of records declared in all EDRMS sites.
Bank-wide Oversight | 8 | Top Panel | Institutional File Plan insights (navigation tile)
Bank-wide Oversight | 12 | Overview Of Edrms Sites | Number of EDRMS SharePoint sites | Feasible Source: CG
Bank-wide Oversight | 30 | Users | Completion of training | Do we have a maintained list of users that have access to edrms who have gone through training? How often is the list updated? Where is it hosted? Does it have the email addresses of the users? | Retain for RAC compliance monitoring. Use Excellerate for staff and the maintained completion source for contractors/consultants, with manual updates until an authoritative integration is available. Show completion against the relevant population.
Bank-wide Oversight | 32 | Documents | Number of documents created / uploaded | Feasible Source: SPO Activity
Bank-wide Oversight | 36 | Documents | Indicator: average monthly storage growth | dependent with S/N 33
Bank-wide Oversight | 38 | Records Declared | Total number of records declared | Same with S/N 4
Bank-wide Oversight | 39 | Records Declared | Total number of users declaring records | feasible Source: EDRMS DB
Bank-wide Oversight | 41 | Records Declared | Indicator: declaration rate against documents
Bank-wide Oversight | 44 | Physical Counterparts | Total number of physical records declared | Same with S/N 5
Bank-wide Oversight | 45 | Physical Counterparts | Total number of users declaring records
Bank-wide Oversight | 63 | The Rest Of Bank-Wide | Bank-wide records declaration trend, cumulative | feasible
Bank-wide Oversight | 64 | The Rest Of Bank-Wide | Records declared in range | date range? Feasible | Show the count of records declared within a user-selected date range, with clear from/to controls and useful preset ranges.
Department Insights | 1 | Department Profile | Department picker driving the whole screen | For All: As long as Department, Division is back filled | Use Department / Office / RM / RO only
Department Insights | 2 | Department Profile | Total number of sites created | Feasible EDRMS DB
Department Insights | 3 | Department Profile | Total number of EDRMS users | Feasible EDRMS DB | Show rounded number of people per department / office / RM. The number should indicate the size of the department / office / RM for context. The number does not need to be exact and therefore should not need to be regularly updated. E.g. CSD approx. 400 / SPSO approx 10.
Department Insights | 5 | Department Profile | Total number of documents in EDRMS | Feasible SPO Activity
Department Insights | 6 | Department Profile | Total number of records declared in EDRMS | Feasible EDRMS DB
Department Insights | 7 | Department Profile | Total number of physical counterparts identified | Feasible EDRMS DB
Department Insights | 9 | Department Profile | Clickable top panel stats
Department Insights | 12 | Users And Activity | Total number of active users | Total Number of Active Users per Department - feasible CG + SPO
Department Insights | 13 | Users And Activity | Used EDRMS in the last 180 days | Total Number of Active Users per Department - feasible CG + SPO
Department Insights | 20 | Overview Of Edrms Sites | Total number of sites created | feasible
Department Insights | 21 | Overview Of Edrms Sites | Total number of documents in EDRMS | feasible
Department Insights | 22 | Overview Of Edrms Sites | Total number of records declared in EDRMS | feasible
Department Insights | 23 | Overview Of Edrms Sites | Total number of physical counterparts identified | feasible
Department Insights | 25 | Overview Of Edrms Sites | Name of sites | feasible
Department Insights | 26 | Overview Of Edrms Sites | Site owners | feasible
Department Insights | 27 | Overview Of Edrms Sites | Number of documents | feasible
Department Insights | 28 | Overview Of Edrms Sites | Number of records | feasible
Department Insights | 29 | Overview Of Edrms Sites | Number of physical counterparts | feasible
Department Insights | 32 | Site Visits | Site visits table, by site | Feasible SPO Activity
Department Insights | 38 | Site Visits | EDRMS Site Type | Feasible EDRMS DB/ CG
Department Insights | 39 | Site Visits | Total number of visitors (external) (#, %) | Need Source to identify if a user is Internal/ External | same as #4 and shows number of Non-ADB people who have accessed the site
Department Insights | 40 | Site Visits | Total number of visitors (internal) (#, %) | Need Source to identify if a user is Internal/ External
Department Insights | 43 | Total Number Of Documents In Edrms | Number of documents created / uploaded | Feasible
Department Insights | 44 | Total Number Of Documents In Edrms | EDRMS Active Sites | Feasible
Department Insights | 45 | Total Number Of Documents In Edrms | Total documents size | Feasible
Department Insights | 46 | Total Number Of Documents In Edrms | Name of sites | Feasible
Department Insights | 48 | Total Number Of Documents In Edrms | Documents size (in GB) | same concern with bank wide oversight | If feasible, yes. If not, can be removed.
Department Insights | 49 | Total Number Of Documents In Edrms | Number of users creating documents | same concern with bank wide oversight | related to item #43
Department Insights | 50 | Records Declaration | Total number of records declared | feasible
Department Insights | 51 | Records Declaration | Total number of users declaring records | feasible
Department Insights | 52 | Records Declaration | Sites with no declared record in 180 days | feasible
Department Insights | 53 | Records Declaration | Total number of records declared | feasible
Department Insights | 54 | Records Declaration | Total number of users declaring records | feasible
Department Insights | 55 | Records Declaration | Total declared record size (in GB) | feasible | If feasible, yes. If not, can be removed.
Department Insights | 58 | Physical Counterpart | Records with a counterpart | feasible
Department Insights | 59 | Physical Counterpart | Total number of records declared | feasible
Department Insights | 60 | Physical Counterpart | Records with a counterpart, by site | feasible
Department Insights | 61 | Physical Counterpart | Total number of records declared | feasible
Department Insights | 62 | Physical Counterpart | Share of records with a counterpart | physical vs records
Department Insights | 77 | Departmental Library Usage, One Per File Plan Category | Library names | feasible
Department Insights | 78 | Departmental Library Usage, One Per File Plan Category | Number of documents | feasible
Department Insights | 79 | Departmental Library Usage, One Per File Plan Category | Number of records declared | feasible
Department Insights | 80 | Departmental Library Usage, One Per File Plan Category | Number of physical counterparts | feasible
Department Insights | 81 | Departmental Library Usage, One Per File Plan Category | Number of users per library

## 4 Agreed with Changes
Build these, but the specification has moved. The comment column is the new specification.
Dashboard | # | Section | Requirement Item | The change RAC asked for | Feasibility Note
Bank-wide Oversight | 1 | Top Panel | Number of active EDRMS SharePoint sites for Department, RM, office Changes: 8/28/2026: Number of active EDRMS SharePoint sites for Department HQ | Show one bank-wide count of active EDRMS-compliant department, office, RM and RO sites, counted once per site and excluding project sites. Keep the organizational breakdown in Department Insights. Backfill and maintain the required site classification metadata. | Feasible Source: EDRMS DB Comments: Need to Backfill Department, Division, and RM values
Bank-wide Oversight | 11 | Overview Of Edrms Sites | Department / office / RM Changes: 8/28/2026: Number of active EDRMS SharePoint sites for Department HQ and this change applies to all same columns as well | Use Department / Office / RM / RO, regardless of physical location (not just HQ). To AvePoint: to confirm how “applies to all same columns” will be implemented. | Feasible Source: EDRMS DB Comments: Need to Backfill Department and Division values
Bank-wide Oversight | 19 | Overview Of Edrms Sites | Indicator: inactive site for 90 days | Retain as a Department Insights metric, not a bank-wide top-panel tile. Define inactivity using the available site-activity window and limit the measure to EDRMS-compliant sites. | Feasible Source: CG Comments: Is this just EDRMS sites?
Bank-wide Oversight | 35 | Documents | Indicator: new documents month on month | Generation of report on total, not the growth (Show periodic snapshots or trend of total documents added, using files created and uploaded and the creation date. Report by Department / Office / RM / RO.) | Need to check feasibiltiy Source: SPO Comments: Files created and uploaded? Or created only? Can have creation date as basis
Bank-wide Oversight | 65 | The Rest Of Bank-Wide | Monthly average in range | This is a report. Not average. Show the number of records declared per month for the selected period, alongside the trend so peak periods and year-on-year patterns can be reviewed. | date range? Average declared records?
Department Insights | 19 | Users And Activity | Training completion rate (%) | Retain for RAC compliance monitoring by selected grouping. Use authoritative training sources where available and allow controlled manual updates until integration is established. | Similar question with Bank wide Oversite S/N 30
Department Insights | 47 | Total Number Of Documents In Edrms | Number of documents created / uploaded | Show document count per site as the breakdown of item 43; ensure that this is not a duplicate the same metric elsewhere. | Feasible
Department Insights | 56 | Records Declaration | Number of records declared per division | Replace division with Department / Office / RM / RO | feasible
Department Insights | 57 | Records Declaration | Number of users declaring records per division | Replace division with Department / Office / RM / RO. Count unique declarers for the selected grouping | feasible

## 5 Clarifications and Answers
The 22 open items, each with an answer drawn from the verified tenant evidence. Confirm the Answer column with RAC and these become decisions.
Dashboard | # | Section | Requirement Item | RAC Comment as written | The question in plain words | Answer / recommendation | Evidence it rests on | Who decides | What to do in the prototype now
Bank-wide Oversight | 2 | Top Panel | Total number of EDRMS users | Show rounded number of people per department / office / RM. The number should indicate the size of the department / office / RM for context. The number does not need to be exact and therefore should not need to be regularly updated. E.g. CSD approx. 400 / SPSO approx 10.. | What counts as an EDRMS user? Someone who has declared a record, or anyone with access to an EDRMS site? | Neither, on RAC's own comment. RAC asked for a rounded headcount per Department / Office / RM / RO to give the unit size as context, not exact and not regularly refreshed. Treat it as an indicative reference value held in a small maintained table, not a measured metric. Keep the measured figure separate: active users, already Agreed at Department Insights #12. | No export holds an ADB workforce headcount. The Cloud Governance users and guest exports carry accounts, not staff numbers. The SharePoint activity user detail is one row per licensed user, 30 rows in the test tenant, of which 8 had any activity. | RAC supplies the rounded headcount list. ADB ITD if a real workforce count is ever wanted. | Build the tile with a manual reference value and label it indicative. Do not derive it from site access.
Bank-wide Oversight | 13 | Overview Of Edrms Sites | Total number of documents | What does AvePoint mean by 'unit'? This shows the total number of documents for the department. | What does AvePoint mean by unit in Total number of documents? | Unit is the grouping row of the table: Department / Office / RM / RO. The figure is the total documents held by that unit's EDRMS-compliant sites, declared or not, counted once per document. | SharePoint site usage export, File Count per site, joined to the Cloud Governance workspace report on Site Id and filtered to rows where EDRMS Site Type is populated (1,032 of 1,209 in the test tenant). | Answered. No RAC decision needed. | Build. Same measure as Bank-wide #3, grouped by unit instead of bank-wide.
Bank-wide Oversight | 14 | Overview Of Edrms Sites | Total number of records declared | Same as item 13 | Is Total number of records declared here the same figure as Bank-wide #4? | Yes. Same measure, different grain: #4 is the bank-wide total, #14 is the same total split by unit. The two must reconcile exactly. | drm-npr PostgreSQL, public.Records, which holds declared records only, about 1,990 rows in the test tenant, joined to the site to unit mapping. | Answered, but depends on the department backfill below. | Build once the unit mapping is loaded. Assert that the unit rows sum to the bank-wide tile.
Bank-wide Oversight | 15 | Overview Of Edrms Sites | Total number of physical counterparts | Dependent on item 14 | Is Total number of physical counterparts here the same figure as Bank-wide #5? | Yes, same measure split by unit, and it follows #14. Note that the bank-wide tile for physical counterparts is itself Deferred, so build the column in the table but keep the top-panel tile off. | drm-npr, the physical counterpart flag on the declared record. | Answered. | Build the table column. Leave the deferred tile off the top panel.
Bank-wide Oversight | 23 | Users | Total number of users, count | Show rounded number of people per department / office / RM. The number should indicate the size of the department / office / RM for context. The number does not need to be exact and therefore should not need to be regularly updated. E.g. CSD approx. 400 / SPSO approx 10. | Is Total number of users the count of users with access to EDRMS sites? | No. Same answer as #2: an indicative rounded headcount per unit, supplied by RAC, not a derived access count. | As #2. | RAC. | One definition serves #2, #23 and Department Insights #3. Do not build three different numbers.
Bank-wide Oversight | 24 | Users | Departments, offices and RMs in the list | See #23 | Should the list show departments, offices and RMs that have no EDRMS site yet? | Yes. Drive the list from RAC's organizational unit list, not from the sites. A unit with no EDRMS site then appears with zeros, which is a compliance finding worth reporting rather than an empty row worth hiding. | The Cloud Governance workspace report Department column is populated on 1,030 of 1,032 EDRMS sites, so it gives the units that have sites. It cannot give the units that do not. | RAC supplies the authoritative unit list. | Build against a unit reference list. Show zero rows rather than dropping them.
Bank-wide Oversight | 25 | Users | Indicator: never accessed EDRMS | If it's feasible? Data to know how many users within the department have not accessed the site, for compliance. | Can we show users who have never accessed EDRMS? | Not as never. The SharePoint activity user detail reports a rolling window of at most 180 days and covers licensed users only, so no source can support the word never. Cloud Governance holds Last Active Time per site, not per user. | Measured: the activity export returned 30 rows, 25 with a last activity date, 8 with any file activity. The window is a report period, not full history. | RAC to accept the wording change. | Replace with No access in the last 180 days. This matches the measure already Agreed at Department Insights #13.
Bank-wide Oversight | 26 | Users | Indicator: not accessed in 90 days | If it's feasible? Data can be used as a site inactivity measure (see item #19) | Can we show users who have not accessed EDRMS in 90 days? | Yes, within the reporting window. Pick one threshold and use it everywhere. Note this also settles the open 90 versus 300 day question on site inactivity: the deck says 90, the metrics document says 300. | SharePoint activity user detail supports 7, 30, 90 and 180 day periods. Cloud Governance Last Active Time gives the site-level equivalent on all 1,032 EDRMS sites, against 381 of 1,918 in the M365 export. | RAC picks the threshold. | Build once the threshold is fixed. Use the same number for user inactivity and site inactivity.
Bank-wide Oversight | 27 | Users | Total number of users (staff) | From Active Directory; is it possible to extract this information (see item #23) | Can users be split into staff, contractors and consultants? | Not from any source we hold. SharePoint, the Graph usage reports and Cloud Governance carry no employment type. The Cloud Governance guest user report carries Job Title and Company name, but only for guests. | Checked across the workspace report's 93 columns, the users export and the guest user export. No employment type field on internal users. | ADB ITD. It needs an Active Directory or HR attribute such as employeeType, and an agreed unique identifier. | Do not build. Align with Department Insights #16 to #18, which RAC already deferred for the same reason.
Bank-wide Oversight | 28 | Users | Total number of users (Contractors) | From Active Directory; is it possible to extract this information (see item #23) | Same as #27, contractors. | See #27. No source. | See #27. | ADB ITD. | Do not build.
Bank-wide Oversight | 29 | Users | Total number of users (Consultants) | From Active Directory; is it possible to extract this information (see item #23) | Same as #27, consultants. | See #27. No source. | See #27. | ADB ITD. | Do not build.
Bank-wide Oversight | 33 | Documents | Documents size (in GB) | If feasible, yes. If not, can be removed. | Is documents size in GB feasible? RAC said keep it if feasible, otherwise remove. | Feasible. Keep it. | Cloud Governance workspace report gives Storage Used (GB) and Storage Quota (GB), populated on all 1,032 EDRMS sites. Microsoft Graph gives size per file. Tenant storage measured at 142.4 GB. Warning for the per-file route: folders return a cumulative size, so the scan must filter to files only or storage doubles. | Answered. | Build. This also unblocks Bank-wide #36, average monthly storage growth, which was made dependent on it.
Bank-wide Oversight | 42 | Records Declared | Number of records declared per division | Replace division with Department / Office / RM / RO. Provide filtering or drill-down rather than a separate division-only measure. | Number of records declared per division. | Division cannot be built. Replace it with Department / Office / RM / RO, with filtering or drill-down rather than a division-only measure. This is the same ruling RAC already made as Agreed with Changes on the equivalent Department Insights items. | The Cloud Governance export carries a Division column and it is empty on all 1,032 EDRMS sites. That is not a missing source, it is no source. | Settled. Apply the rename everywhere. | Build against the unit grouping.
Bank-wide Oversight | 43 | Records Declared | Number of users declaring records per division | Replace division with Department / Office / RM / RO. Count unique people declaring records for the selected grouping. | Number of users declaring records per division. Does a user have a division, or does it come from the site or document? | Users carry no division and no department in any source we hold. Attribute the declarer to the unit of the site the record was declared in, and count unique people per unit. | Division empty on all 1,032 rows. Department attaches to the site, confirmed feasible by dev on 10 August: documents inherit through SiteUrl, no migration needed. | RAC to accept site-based attribution. | Build as unique declarers per unit, attributed by site.
Bank-wide Oversight | 46 | Physical Counterparts | Share of records with a counterpart | visualization: graph or just a tile containg % | Share of records with a counterpart: is it physical against all records, and should it be a chart or a tile? | Physical counterparts divided by declared records. Show it as a tile carrying the percentage with the two base counts beside it, not a chart. A single ratio does not need a visual, and showing the bases keeps it reconcilable. | Both bases come from drm-npr and are already Agreed at #44 and #38. | RAC to confirm the presentation. | Build as a tile.
Bank-wide Oversight | 61 | The Rest Of Bank-Wide | Comparison, three named ratios: Active users against documents | Replace active users with the available contextual workforce count by Department / Office / RM / RO, if sourced authoritatively, and compare it with document totals. | Active users against documents. What is an active user? | Two different things are being asked for, so publish both and label each with its denominator. Active user, measurable: a user with SharePoint activity above zero in the chosen window. Contextual headcount, RAC's preference in the comment: the rounded unit size from #2. Do not blend them into one unlabelled ratio. | Measured in the test tenant: 8 of 30 licensed users had activity above zero. The contextual headcount has no source and must be supplied. | RAC picks which denominator the headline ratio uses. | Hold until #2 is settled. The definition is the same blocker.
Bank-wide Oversight | 62 | The Rest Of Bank-Wide | Comparison, three named ratios: Active users against Records declared | Compare the contextual workforce count by Department / Office / RM / RO with declared records, if an authoritative workforce source is available. | Active users against records declared. Same question. | Same answer as #61. Also note the declarer count is already Agreed at #39 and is exact, so the ratio's numerator is not in doubt, only its denominator. | drm-npr gives unique declarers directly. | RAC, with #61. | Hold with #61.
Department Insights | 4 | Department Profile | Total number of site visitors | Can this be a number of unique users who accessed the site and is not with ADB email? | Total number of site visitors: can it be unique users who accessed the site without an ADB email? | Yes, with a wording change. Report unique visitors, split internal and external by email domain, rather than visits. Page View Count counts visits, not people, so it cannot answer the question as asked. | Microsoft Graph site analytics returns actorCount, unique viewers, measured at 12 on one test site against actionCount 5,535. The Cloud Governance guest user report identifies external accounts, and the workspace report carries External Sharing for Site. | RAC to confirm that external means a non-ADB email domain. | Build as unique visitors. This also serves #39 and #40, both already Agreed, and makes #31 the duplicate RAC marked Not Required.
Department Insights | 10 | Department Profile | Approved SharePoint site, library and folder convention | Can this be just a link to the department's approved site convention to make it easily accessible for users | Approved site, library and folder convention: can it be a link to the unit's convention rather than a data model? | Yes, and that is the right answer. No source holds the naming convention, so modelling it would mean inventing data. A maintained link per unit is honest and useful. | Checked: no convention field in the workspace report, the request report or the term store extract. | RAC maintains the link list. | Build as a reference link field per unit.
Department Insights | 11 | Department Profile | Go-Live date | Can this be for manual input to record when a site was provisioned to a department | Go-live date: can it be manual input recording when a site was provisioned to a unit? | Yes, manual for now. There is no reliable automated source. Cloud Governance Created Time records when the SharePoint site was created, not when it became EDRMS; for a converted site those are different dates and no column in the 93-column export records the conversion. The likely automated home is the Cloud Governance Job monitor, whose Site manual import and Apply profile for site jobs are timestamped, but that is unproven. | Every date column in the workspace report was checked. This correction is already recorded in the project status: Created Time was first written up as go-live and that was an inference, not a measurement. | RAC maintains the register. AvePoint to confirm whether Job monitor can supply it. | Build as a manual field. Do not label site creation as go-live.
Department Insights | 41 | Site Visits | Total number of access requests granted (#, %) | Is it possible to know how many access requests are granted, could be used as a basis to review the library's restriction | Total number of access requests granted: what is meant, and can it inform a review of library restrictions? | Partly buildable, and it must be scoped. Cloud Governance holds a Request report with Request ID, Status, Approval Stage, Request Type and Target Object, so requests routed through Cloud Governance can be counted and split by outcome. Native SharePoint access requests are not in it; those need audit log data, a different Graph surface, which was cut from scope earlier as S/N 120. | The request report export is in the repo and its columns are verified. | RAC to accept the narrower scope. | Build as Cloud Governance access requests only, and say so on the panel. Note RAC marked the denied counterpart, #42, Not Required, so show granted alone.
Department Insights | 82 | Departmental Library Usage, One Per File Plan Category | Indicators per library, per division | Replace division with Department / Office / RM / RO | Indicators per library, per division. | Division cannot be built. Replace with Department / Office / RM / RO, as ruled on the equivalent items. A further limit applies: no per-library activity feed exists, only per site, so library indicators must be counts of documents, records and counterparts rather than usage. | Division empty on all 1,032 rows. The most-used libraries tile was cut earlier for exactly this reason. | RAC to accept the counts-only scope. | Build counts per library grouped by unit. Do not promise library usage.

## 6 Not Required - Remove
Remove these from the prototype. Most are duplicates of a measure kept elsewhere.
Dashboard | # | Section | Requirement Item | Why it comes off | Feasibility Note
Bank-wide Oversight | 16 | Overview Of Edrms Sites | Indicator: no. of sites created | Remove as a duplicate of item 1. All dashboard counts must be limited to EDRMS-compliant sites. | Feasible Source: CG Comments: Is this just EDRMS sites?
Bank-wide Oversight | 34 | Documents | Number of users creating documents | Remove. This overlaps with document totals and does not support the agreed RAC definition of an EDRMS user. | Users creating documents in SPO? Not including people uploading in SPO? Need to check feasibility if can retrieve in SPO
Bank-wide Oversight | 37 | Documents | Per division breakdown | Remove the separate per-division breakdown. Use Department / Office / RM / RO groupings | If all can be retrieved, we need a division value for the documents, if these are declared documents, we need to source it from the EDRMS DB (provided that division backfill is done), if not a declared record, the file must have a metadata for division, if not, we can base it of the site it is hosted in
Bank-wide Oversight | 40 | Records Declared | Indicator: zero record declarations | This can be achieved by #38 & #39 | is this zero records in an edrms site? Department? Division?
Bank-wide Oversight | 47 | Physical Counterparts | Per division, two columns | Remove the separate division columns. Use Department / Office / RM / RO filters | per division physical? Feasible
Bank-wide Oversight | 60 | The Rest Of Bank-Wide | Comparison, three named ratios: Documents against Records declared | Same as item 41? | Feasible
Department Insights | 14 | Users And Activity | No access in EDRMS compliant sites, last 180 days | Remove as duplicative of the agreed inactivity measure in item 13. | Opposite of S/N 13 - feasible
Department Insights | 15 | Users And Activity | Never accessed EDRMS compliant sites | Remove. The available reporting window cannot support the word 'never', and item 13 provides the needed inactivity view.
Department Insights | 31 | Site Visits | Total number of visitors | Same as #4
Department Insights | 33 | Site Visits | Page View Count | Removed by RAC decision. | Feasible SPO Activity
Department Insights | 34 | Site Visits | Visited Page Count | Removed by RAC decision. | Feasible SPO Activity
Department Insights | 35 | Site Visits | Name of sites | Same as #32 | Feasible SPO Activity
Department Insights | 36 | Site Visits | Page View Count | Removed by RAC decision. | Feasible SPO Activity
Department Insights | 37 | Site Visits | Visited Page Count | Removed by RAC decision. | Feasible SPO Activity
Department Insights | 42 | Site Visits | Total number of access requests denied (#, %) | Removed by RAC decision. | Need more details on what is meant by this
Department Insights | 63 | Physical Counterpart | Per division, two columns | Remove separate division columns. | per division physical? Feasible

## 7 Deferred
Out of scope for this release. Grouped by the dependency that unblocks them.
Blocking dependency | Dashboard | # | Section | Requirement Item | Reason for deferral
A. Retention and Disposal / Records Disposition feature release | Bank-wide Oversight | 5 | Top Panel | Total number of physical counterparts identified | Defer until the Retention and Disposal dashboard and related process are defined. Later reporting should distinguish overdue, due today and upcoming records, and account for retention extensions.
A. Retention and Disposal / Records Disposition feature release | Bank-wide Oversight | 6 | Top Panel | Total number of records due for disposal | Retain as a future navigation link, but do not include it in the current top panel until the Retention and Disposal dashboard is established.
A. Retention and Disposal / Records Disposition feature release | Bank-wide Oversight | 49 | Records Due For Disposal | Number of records due for disposal | Defer until the dashboard for Retention and Disposal is developed.
A. Retention and Disposal / Records Disposition feature release | Bank-wide Oversight | 50 | Records Due For Disposal | Next due date for disposal | Defer until the dashboard for Retention and Disposal is developed.
A. Retention and Disposal / Records Disposition feature release | Bank-wide Oversight | 51 | Records Due For Disposal | With physical counterpart? | Defer until the dashboard for Retention and Disposal is developed.
A. Retention and Disposal / Records Disposition feature release | Bank-wide Oversight | 52 | Records Due For Disposal | Indicator: upcoming next quarter | Defer until the dashboard for Retention and Disposal is developed.
A. Retention and Disposal / Records Disposition feature release | Bank-wide Oversight | 53 | Records Due For Disposal | Disposal approver | Defer until the dashboard for Retention and Disposal is developed.
A. Retention and Disposal / Records Disposition feature release | Bank-wide Oversight | 54 | Records Due For Disposal | Status (Approved) | Defer until the dashboard for Retention and Disposal is developed.
A. Retention and Disposal / Records Disposition feature release | Bank-wide Oversight | 55 | Records Due For Disposal | Status (Declined) | Defer until the dashboard for Retention and Disposal is developed.
A. Retention and Disposal / Records Disposition feature release | Bank-wide Oversight | 56 | Records Due For Disposal | Status (Extended) | Defer until the dashboard for Retention and Disposal is developed.
A. Retention and Disposal / Records Disposition feature release | Bank-wide Oversight | 57 | Records Due For Disposal | Indicator: records disposed month on month | Defer until the dashboard for Retention and Disposal is developed.
A. Retention and Disposal / Records Disposition feature release | Bank-wide Oversight | 58 | Records Due For Disposal | Indicator: overdue actions, pending approvals | Defer until the dashboard for Retention and Disposal is developed.
A. Retention and Disposal / Records Disposition feature release | Bank-wide Oversight | 59 | Records Due For Disposal | Indicator: disposal completion rate | Defer until the dashboard for Retention and Disposal is developed.
A. Retention and Disposal / Records Disposition feature release | Department Insights | 8 | Department Profile | Total number of records due for disposal | Defer until Records Disposition feature is released.
A. Retention and Disposal / Records Disposition feature release | Department Insights | 24 | Overview Of Edrms Sites | Total number of records due for disposal within 12 months | Defer to the Retention and Disposal dashboard
A. Retention and Disposal / Records Disposition feature release | Department Insights | 30 | Overview Of Edrms Sites | Number of records due for disposal | Defer to the Retention and Disposal dashboard
A. Retention and Disposal / Records Disposition feature release | Department Insights | 65 | Disposal | Records due for disposal within 3 months | Defer until Records Disposition feature is released.
A. Retention and Disposal / Records Disposition feature release | Department Insights | 66 | Disposal | Records due for disposal within 6 months | Defer until Records Disposition feature is released.
A. Retention and Disposal / Records Disposition feature release | Department Insights | 67 | Disposal | Records due for disposal within 12 months | Defer until Records Disposition feature is released.
A. Retention and Disposal / Records Disposition feature release | Department Insights | 68 | Disposal | Number of records due for disposal | Defer until Records Disposition feature is released.
A. Retention and Disposal / Records Disposition feature release | Department Insights | 69 | Disposal | Next due date for disposal | Defer until Records Disposition feature is released.
A. Retention and Disposal / Records Disposition feature release | Department Insights | 70 | Disposal | With physical counterpart? | Defer until Records Disposition feature is released.
A. Retention and Disposal / Records Disposition feature release | Department Insights | 71 | Disposal | Disposal approver | Defer until Records Disposition feature is released.
A. Retention and Disposal / Records Disposition feature release | Department Insights | 72 | Disposal | Status (Approved) | Defer until Records Disposition feature is released.
A. Retention and Disposal / Records Disposition feature release | Department Insights | 73 | Disposal | Status (Declined) | Defer until Records Disposition feature is released.
A. Retention and Disposal / Records Disposition feature release | Department Insights | 74 | Disposal | Status (Extended) | Defer until Records Disposition feature is released.
A. Retention and Disposal / Records Disposition feature release | Department Insights | 75 | Disposal | Total number of records disposed, per year and month | Defer until Records Disposition feature is released.
A. Retention and Disposal / Records Disposition feature release | Department Insights | 76 | Disposal | Total disposed record size (in GB) | Defer until Records Disposition feature is released.
B. Project Insights and sovereign / nonsovereign project sites | Bank-wide Oversight | 9 | Top Panel | Total number of active EDRMS SharePoint sites for Sovereign projects | Defer until sovereign project sites and Project Insights are implemented and a reliable site-to-project classification is available.
B. Project Insights and sovereign / nonsovereign project sites | Bank-wide Oversight | 10 | Top Panel | Total number of active EDRMS SharePoint sites for Nonsovereign projects | Defer until nonsovereign project sites and Project Insights are implemented and a reliable site-to-project classification is available.
B. Project Insights and sovereign / nonsovereign project sites | Bank-wide Oversight | 20 | Sovereign And Nonsovereign | Sovereign project site list, all columns | Defer until sovereign project sites, the Project Insights dashboard and supporting site-to-project data are available.
B. Project Insights and sovereign / nonsovereign project sites | Bank-wide Oversight | 21 | Sovereign And Nonsovereign | Nonsovereign project site list, all columns | Defer until nonsovereign project sites, the Project Insights dashboard and supporting site-to-project data are available.
B. Project Insights and sovereign / nonsovereign project sites | Bank-wide Oversight | 22 | Sovereign And Nonsovereign | Project rows clickable into Project Insights | Defer the drill-through behavior until Project Insights is implemented.
C. Physical records handover to RAC | Bank-wide Oversight | 48 | Physical Counterparts | Indicator: physical counterpart completion rate (turned over to RAC) | Defer until the physical records management or Records and Archives Holdings capability records handover to RAC.
C. Physical records handover to RAC | Department Insights | 64 | Physical Counterpart | Physical counterpart completion rate (turned over to RAC) | Defer until the physical records management or Records and Archives Holdings capability records handover to RAC.
D. Site lifecycle, workforce and programme items | Bank-wide Oversight | 7 | Top Panel | Retention and disposal insights (navigation tile) | Retain as a future navigation link, but do not include it in the current top panel until the Institutional File Plan dashboard is established.
D. Site lifecycle, workforce and programme items | Bank-wide Oversight | 17 | Overview Of Edrms Sites | Indicator: no. of sites deleted | Defer as a possible future lifecycle metric. If retained, limit it to EDRMS-compliant sites and place it in Department Insights rather than the bank-wide top panel.
D. Site lifecycle, workforce and programme items | Bank-wide Oversight | 18 | Overview Of Edrms Sites | Indicator: no. of sites archived | Defer until EDRMS sites begin moving to inactive or archived status. If retained, limit it to EDRMS-compliant sites and show it in Department Insights.
D. Site lifecycle, workforce and programme items | Bank-wide Oversight | 31 | Users | Onboarded since go-live | Defer until RAC maintains an authoritative onboarding register and a reliable EDRMS go-live date for each site or unit.
D. Site lifecycle, workforce and programme items | Department Insights | 16 | Users And Activity | Total number of staff | to align with the Bank-wide tab #27-29
D. Site lifecycle, workforce and programme items | Department Insights | 17 | Users And Activity | Total number of contractors (#, %) | to align with the Bank-wide tab #27-29
D. Site lifecycle, workforce and programme items | Department Insights | 18 | Users And Activity | Total number of consultants (#, %) | to align with the Bank-wide tab #27-29
D. Site lifecycle, workforce and programme items | Department Insights | 83 | Other Panels On This Dashboard | Programme dates | To finalize programmes to be included (go-live, site audit. etc.)

## 8 Not Yet Decided
Four of the six dashboards carry no decisions in Checker 7. Nothing on them is finalized.
Dashboard | State in Checker 7 | What is needed
3 Project Insights | Content sheet only. No RAC Decision column. | A RAC pass. Note that every sovereign and nonsovereign item on Bank-wide was deferred pending this dashboard and a reliable site to project classification.
4 Institutional File Plan | Content sheet only. No RAC Decision column. | A RAC pass. Bank-wide #8, the navigation tile into it, is Agreed, so the route in exists while the destination is unspecified.
5 Retention and Disposal | Content sheet only. No RAC Decision column. | A RAC pass, and the definition of due for disposal: today, or the next 30, 60 or 90 days. This is the single dependency blocking 25 deferred items across both decided dashboards.
6 Records and Archive Holdings | Content sheet only. No RAC Decision column. | A RAC pass. Every measure on it currently reads Not captured in the prototype and a notice says it is not yet specified.