## Records and Archive Holdings
Records and Archive Holdings
REFERENCE DECK:
https://avepointcrm.sharepoint.com/:p:/r/sites/Gen_ADB_DRM_Internal/Shared%20Documents/General/04.%20Requirement%20
# | Requirement Items | Type | In the prototype? | Slide | Why it is not there | What it needs before it can be built | Question to the client
THE DASHBOARD ITSELF
1 | Records and Archive Holdings, as a key view | Dashboard | Yes | s13, s14 |  | Present, and since 24 Aug it is a built screen rather than a stub. Every measure below still needs its source before it carries a real figure. | Q17
2 | The two tables drawn with the client's own column headings | Panel | Yes | s68, s69 |  | Shape and column names are the client's own. Content is illustrative. | Q17
3 | Physical counterparts identified | Indicator | Yes | s68 |  | SOURCED. Declared records in drm-npr flagged as having a paper counterpart. The one figure on this dashboard with a real parent.
SLIDE 67, THE OVERVIEW SCREEN
4 | Total storage and retrieval requests | Tile | Yes | s67 |  | The client's own published total. Needs the eServe request feed to become live. | Q17
5 | Total storage activities | Tile | Yes | s67 |  | The client's own published total. Needs RAC's holdings register to become live. | Q17
6 | Total staff supported | Tile | Yes | s67 |  | The client's own published total. Needs the requestor on the eServe request. | Q17
7 | Total retrieval activities | Tile | Yes | s67 |  | The client's own published total. Needs RAC's retrieval record. | Q17
8 | Storage activities donut: boxes and folders stored | Chart | Yes | s67 |  | The 92 / 8 split the client printed. Needs RAC's holdings register. | Q17
9 | Retrieval activities donut: archived and records material | Chart | Yes | s67 |  | The 91 / 9 split the client printed. Needs RAC's retrieval record. | Q17
10 | Storage and retrieval requests, by month | Chart | Yes | s67 |  | Drawn. The figure is illustrative, a split of the client's own s67 total, not a measurement. Needs a dated eServe request extract. | Q17
11 | Storage and retrieval activities, by month | Chart | Yes | s67 |  | Drawn. The figure is illustrative, a split of the client's own s67 total, not a measurement. Needs a dated holdings register. | Q17
12 | Retrieval counts material removed from the holdings, as processed from eServe, not requests raised | Definition | Yes | s67 |  | The client's own note on s67, now stated on the screen so the definition travels with the figure. | Q17
SLIDE 68, STORAGE
13 | Location, as Archives Room / Records Center / Offsite Storage | Table column | Yes | s68 |  | The client's three locations. No system carries which one a box is in. Check the Opus Locations export, and confirm it is a picklist not free text. | Q17
14 | No. of requests | Table column | Yes | s68 |  | Drawn. The figure is illustrative, a split of the client's own s67 total, not a measurement. Needs the eServe request extract. Opus reports physical records requests. | Q17
15 | Total number of requestors (departments) | Table column | Yes | s68 |  | Drawn. The figure is illustrative, a split of the client's own s67 total, not a measurement. Check whether the Opus requestor carries a department. | Q17
16 | Total number of requestors (RMs) | Table column | Yes | s68 |  | Drawn. The figure is illustrative, a split of the client's own s67 total, not a measurement. Check the Opus requests export. | Q17
17 | Total number of boxes stored | Table column | Yes | s68 |  | Drawn. The figure is illustrative, a split of the client's own s67 total, not a measurement. Check the Opus Physical records Explorer export for a box type. | Q17
18 | Total number of folders stored | Table column | Yes | s68 |  | Drawn. The figure is illustrative, a split of the client's own s67 total, not a measurement. Check the same Opus Explorer export. | Q17
19 | Remarks | Table column | Yes | s68 |  | Carries text, not a figure, because it is a note somebody maintains. ASK whether Remarks is captured anywhere. | Q17
20 | Indicator: new boxes and folders month on month per department | Indicator | Yes | s68 |  | Drawn. The figure is illustrative, a split of the client's own s67 total, not a measurement. Drawn as two cuts, by month and by department. Needs an accession date and a department per item. | Q17
21 | No. and list of outstanding / pending requests | Indicator | Yes | s68 |  | The count is drawn. THE LIST IS NOT. Needs the eServe request extract carrying request state; Opus does show pending and overdue loan counts. | Q17
22 | Physical counterparts identified but not transferred | Indicator | Yes | s68 |  | Half sourced. The counterparts identified are real, from EDRMS. The transfer event is recorded nowhere, so the difference cannot yet be computed. | Q6, Q17
23 | Room capacity and % available storage capacity | Chart | No | s68 | REMOVED ON 24 AUGUST, deliberately. A 65 / 80 / 45 per cent capacity chart stood here and was taken out: the slide asks US whether capacity CAN be included, and drawing a bar answered the client's own question with an invented number. | A capacity figure per location from RAC, and a definition of what full means. Check the Opus Locations export for a capacity field, then answer the question. | Q17
SLIDE 69, RETRIEVAL
24 | Location | Table column | Yes | s69 |  | As s68. Opus Locations. | Q17
25 | No. of requests | Table column | Yes | s69 |  | Drawn. The figure is illustrative, a split of the client's own s67 total, not a measurement. Opus requests export. A retrieval is a loan in Opus terms. | Q17
26 | Total number of requestors (departments / RMs) | Table column | Yes | s69 |  | Drawn. The figure is illustrative, a split of the client's own s67 total, not a measurement. Opus requests export. | Q17
27 | Total number of boxes retrieved | Table column | Yes | s69 |  | Drawn. The figure is illustrative, a split of the client's own s67 total, not a measurement. Opus requests export, loan type. | Q17
28 | Total number of folders retrieved | Table column | Yes | s69 |  | Drawn. The figure is illustrative, a split of the client's own s67 total, not a measurement. Opus requests export. | Q17
29 | Status: Loan, Return to owner, For Disposal | Table column | Yes | s69 |  | Carried as the MIX per location, not one value per row, because the client's column names a vocabulary. Check the Opus status values against their three words. | Q17
30 | Remarks | Table column | Yes | s69 |  | As s68. ASK. | Q17
31 | Indicator: retrieval requests and boxes / folders retrieved month on month per department | Indicator | Yes | s69 |  | Drawn. The figure is illustrative, a split of the client's own s67 total, not a measurement. Drawn as two cuts, by month and by department. Needs the Opus requests export with dates and department. | Q17
32 | No. and list of outstanding / pending requests | Indicator | No | s69 | Not drawn on the retrieval screen. The s68 pending panel covers storage requests and records awaiting transfer, not outstanding retrievals. | The eServe request extract carrying retrieval request state. The figure is already held in the data as RA_PENDING_RETR and can be drawn in one edit. | Q17
33 | No. of boxes / folders disposed | Indicator | Yes | s69 |  | Drawn. The figure is illustrative, a split of the client's own s67 total, not a measurement. Drawn as a table by location. Needs RAC's disposal register; Opus shows pending destruction. | Q17
34 | Can room activities update capacity and freed up storage? | Question | No | s69 | An open question the client put to US, not a requirement to build. It is NOT answered. The freed capacity column that once sat beside the disposal table went with the capacity chart on 24 August, for the same reason. | The client's decision on the definition, then the capacity source. Answer it once the Opus Locations export is read. | Q17
SLIDE 67, WHAT THE CLIENT SAID ABOUT THIS DASHBOARD
35 | Retrieval as processed from eServe | Source | No | s67 | eServe has never been connected to this project and nobody has named an owner. The DEFINITION it implies is now honoured on the screen; the FEED is not. | ASK. Is eServe the retrieval system of record, and who owns it. | Q17
36 | What is available in Opus and how we can apply it | Source | No | s67 | The client asked this on s67. It was closed on 17 Aug as 'nothing from Opus', and nothing on this dashboard is taken from Opus or from the IR Dashboard. | Run the seven exports in OPUS_EXPORT_INSTRUCTIONS.md, then put it back to the client. | Q17
TAKEN OFF THE DASHBOARD ON 24 AUGUST, RECORDED SO THE REMOVAL IS NOT SILENT
37 | Unverified holdings | Tile | No | none | Removed. It appears nowhere in s67, s68 or s69. The standing rule since 17 August is that undrawn is enough on all six dashboards. | A client requirement asking for it. None exists.
38 | Missing items | Tile | No | none | Removed, same reason. | A client requirement asking for it. None exists.
39 | Due for verification | Tile | No | none | Removed, same reason. | A client requirement asking for it. None exists.
40 | Legacy files | Tile | No | none | Removed, same reason. | A client requirement asking for it. None exists.
41 | 1,840 boxes, 9,260 folders and 342 requests as headline figures | Figure | No | none | Removed. Invented outright, and reconciling with nothing. The dashboard is now re-based on the eight totals the client themselves printed on s67. | Nothing. These should not come back.